## Sheet1
MUST HAVE
ID | SPECIFICATION | DEVELOPMENT TIME (HRS) | TEST TIME (HRS) | STATUS
VERSION1
M1 / M2 | Determine which exchange has smallest distance and output its ID | 0.5 | 0.5
M1 / C2 | If both distances are the same, output first ID | 0.25 | 0.5
M2 | Calculate exchange distance as x + y location | 0.25 | 0.5
M3 | Exchange IDs must be unique | 0.25 | 0.5
M3 | Validate exchange ID format "ex:[0-9]:[0-9]" | 0.25 | 0.5
M4 | Validate grid input as greater or equal to 0 and equal or less than 100,000 | 0.25 | 0.5
M6 | Let User input exchange format as an ID, x location, and y location | 1 | 1
M6 | Let User input 2 exchanges | 0.5 | 0.5
VERSION2
M7 | Whan calculate button clicked: Display grid where each grid cell that contains an | 0.5 | 0.5
exchange will display exchange ID and the distance from customer
M8 | Display customer in top left cell of grid | 0.25 | 0.5
VERSION3
M9.1 | Let user input up to 99 exchanges [add button] | 0.5 | 0.5
M9.2 | Add exchange button | 0.5 | 0.5
M9.3 | Remove exchange2 row | 0.5 | 0.5
VERSION4
M10.1 | Let user input capacity of each exchange | 0.5 | 0.5 | TESTING
M10.2 | Validate capactiy as greater than or equal to 0 and lesser than or equal to 999 | 0.5 | 0.5 | TESTING
| TOTAL | 6.5 | 8
|  | GRAND TOTAL | 14.5