## Sheet1
|  | Development estimation (hours) | Testing estimation (hours) | Done
| (Setup) | 0.5
Specification
M1 / M2 | Determine which exchange has smallest distance and output its ID | 0.5 | 0.5 | yes
M1 / C2 | If both distances are the same, output first ID | 0.5 | 0.5 | yes
M2 | Calculate exchange distance as x + y location | 0.5 | 0.5 | yes
M3 | Exchange IDs must be unique | 0.5 | 0.5 | yes
M3 | Validate exchange ID format "ex:[0-9]:[0-9]"
M4 | Let User input exchange format as an ID, x location, and y location | 0.5 | 0.5 | yes
M4 | Let User input 2 exchanges
M4 | Validate grid input as greater or equal to 0 and equal or less than 100,000 | 0.5 | 0.5 | yes
M6 | Let user input capacity of each exchange | 0.5 | 0.5 | TODO
C1 | Display “Home Address” at the (0,0) location on grid | !!!!!!!!!!!!!!!!!!!!!!!!!!!!!!!!!!!!!!!!!!! | !!!!!!!!!!!!!!!!!!!!!!!!!!!!!!!!!!! | maybe
C3 | Create and display visual 2D grid | Estimations need to be revised for the next version of the specs. |  | maybe
C3 | Display exchange ID at grid location |  |  | maybe
C4 | Use capacity of exchange when determining which to choose if equidistant |  |  | TODO
| Total | 4 | 1.5
This is just a default value as we need to assess our original estimates