## Sheet1
| MUST HAVE |  |  |  |  | COULD HAVE
ID | SPECIFICATION | DEVELOPMENT TIME | TEST TIME |  | ID | SPECIFICATION | DEVTIME | TEST TIME
VERSION1 VERSION1 VERSION1 VERSION1 VERSION1 VERSION1 VERSION1 VERSION1 VERSION1 VERSION1 VERSION1 VERSION1 VERSION1 VERSION1 VERSION1 VERSION1 VERSION1 |  |  |  |  | VERSION1 VERSION1 VERSION1 VERSION1 VERSION1 VERSION1 VERSION1 VERSION1 VERSION1 VERSION1 VERSION1 VERSION
M1 / M2 | Determine which exchange has smallest distance and output its ID | 0.5 |  |  | C1 | Display “Home Address” at the (0,0) location on grid | 0.5 | 0.5 | TODO
M1 / C2 | If both distances are the same, output first ID | 0.25 |  |  | C3 | Create and display visual 2D grid | 0.5 | 0.5 | TODO
M2 | Calculate exchange distance as x + y location | 0.25 |  |  | C3 | Display exchange ID at grid location | 0.5 | 0.5 | TODO
M3 | Exchange IDs must be unique | 0.25 |  |  | VERSION4 VERSION4 VERSION4 VERSION4 VERSION4 VERSION4 VERSION4 VERSION4 VERSION4 VERSION4 VERSION4 VERSION
M3 | Validate exchange ID format "ex:[0-9]:[0-9]" | 0.25 |  |  | C4 | Use capacity of exchange when determining which to choose if equidistant |  |  | TODO
M4 | Validate grid input as greater or equal to 0 and equal or less than 100,000 | 0.25 |  |  |  | TOTAL | 1.5 | 0
M6 | Let User input exchange format as an ID, x location, and y location | 1
M6 | Let User input 2 exchanges | 0.5
VERSION2 VERSION2 VERSION2 VERSION2 VERSION2 VERSION2 VERSION2 VERSION2 VERSION2 VERSION2 VERSION2 VERSION2 VERSION2 VERSION2 VERSION2 VERSION2 VERSION2
M8 | Display empty grid on load |  |  | TODO
M9 | Whan calculate button clicked: Each grid cell that contains an exchange will display
| exchange ID and the distance from customer |  |  | TODO
VERSION3 VERSION3 VERSION3 VERSION3 VERSION3 VERSION3 VERSION3 VERSION3 VERSION3 VERSION3 VERSION3 VERSION3 VERSION3 VERSION3 VERSION3 VERSION3 VERSION3
M7 | Let user input up to 99 exchanges |  |  | TODO
VERSION4 VERSION4 VERSION4 VERSION4 VERSION4 VERSION4 VERSION4 VERSION4 VERSION4 VERSION4 VERSION4 VERSION4 VERSION4 VERSION4 VERSION4 VERSION4 VERSION4
M10 | Let user input capacity of each exchange | 0.5 |  | TODO
| TOTAL | 3.25 | 0